## Project Rating Sheet
Benefits/Efforts Project Rating Sheet
|  |  |  | Benefit | [7 empty] | Effort | [7 empty] | Remarks
ID | Project Title | Owner | Type | Revenue Enhancement | Reduce Cost | Increase Speed | Strategic Alignment | Amount of Client "Pain" | Client Value | Business Unit Impact | Total Benefit | Personnel Requirements (Ave FTE) | Project Duration (wks) | Budget Avail | Capital Investment | Project Risk | Business Unit Impact | Total Effort | Recommended Priority (from Matrix Chart)
| Importance Weighting |  |  | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.15 | 0.1 | 1 | 0.2 | 0.2 | 0.15 | 0.15 | 0.15 | 0.15 | 1
1 | Project 1 |  |  | 0 | 9 | 6 | 6 | 9 | 6 | 3 | 5.7 | 6 | 3 | 0 | 0 | 6 | 3 | 3.15 | 12.55
2 | Project 2 |  |  | 0 | 9 | 9 | 6 | 6 | 6 | 9 | 6.3 | 3 | 6 | 0 |  | 0 | 3 | 2.25 | 14.05 |  | Do not cut or copy formulas from one row to another.
3 | Project 3 |  |  | 3 | 6 | 3 | 9 | 9 | 0 | 3 | 4.8 | 6 | 3 | 3 | 0 | 0 | 0 | 2.25 | 12.55 |  | This may result in garbled results.
4 | Project 4 |  |  | 0 | 3 | 6 | 6 | 3 | 3 | 6 | 3.75 | 0 | 3 | 0 |  | 0 | 6 | 1.5 | 12.25
5 | Project 5 |  |  | 0 | 3 | 0 | 3 | 0 | 0 | 9 | 1.8 | 6 | 9 | 0 |  | 6 | 9 | 5.25 | 6.55 |  | Weighting factors can be changed.
6 | Project 6 |  |  | 0 | 0 | 3 | 3 | 0 | 0 | 6 | 1.5 | 0 | 3 | 0 | 0 | 0 | 6 | 1.5 | 10 |  | Perform an AHP to calculate new weights.
7 | Project 7 |  |  | 0 | 9 | 6 | 3 | 0 | 0 | 9 | 3.6 | 9 | 9 | 0 |  | 6 | 9 | 5.85 | 7.75
8 | Project 8 |  |  | 0 | 0 | 9 | 3 | 9 | 9 | 3 | 4.8 | 9 | 6 | 0 |  | 6 | 3 | 4.35 | 10.45
9 | Project 9 |  |  | 0 | 3 | 6 | 6 | 9 | 9 | 3 | 5.25 | 3 | 3 | 0 |  | 0 | 3 | 1.65 | 13.6
10 | Project 10 | [9 empty] | 0 | [6 empty] | 0 | 0
11 | Project 11 | [9 empty] | 0 | [6 empty] | 0 | 0
12 | Project 12 | [9 empty] | 0 | [6 empty] | 0 | 0
13 | Project 13 | [9 empty] | 0 | [6 empty] | 0 | 0
14 | Project 14 | [9 empty] | 0 | [6 empty] | 0 | 0
15 | Project 15 | [9 empty] | 0 | [6 empty] | 0 | 0
16 | Project 16 | [9 empty] | 0 | [6 empty] | 0 | 0
17 | Project 17 | [9 empty] | 0 | [6 empty] | 0 | 0
18 | Project 18 | [9 empty] | 0 | [6 empty] | 0 | 0
19 | Project 19 | [9 empty] | 0 | [6 empty] | 0 | 0
20 | Project 20 | [9 empty] | 0 | [6 empty] | 0 | 0
21 | Project 21 | [9 empty] | 0 | [6 empty] | 0 | 0
22 | Project 22 | [9 empty] | 0 | [6 empty] | 0 | 0
23 | Project 23 | [9 empty] | 0 | [6 empty] | 0 | 0
24 | Project 24 | [9 empty] | 0 | [6 empty] | 0 | 0
25 | Project 25 | [9 empty] | 0 | [6 empty] | 0 | 0
26 | Project 26 | [9 empty] | 0 | [6 empty] | 0 | 0
27 | Project 27 | [9 empty] | 0 | [6 empty] | 0 | 0
28 | Project 28 | [9 empty] | 0 | [6 empty] | 0 | 0
29 | Project 29 | [9 empty] | 0 | [6 empty] | 0 | 0
30 | Project 30 | [9 empty] | 0 | [6 empty] | 0 | 0
31 | Project 31 | [9 empty] | 0 | [6 empty] | 0 | 0
32 | Project 32 | [9 empty] | 0 | [6 empty] | 0 | 0
33 | Project 33 | [9 empty] | 0 | [6 empty] | 0 | 0
34 | Project 34 | [9 empty] | 0 | [6 empty] | 0 | 0
35 | Project 35 | [9 empty] | 0 | [6 empty] | 0 | 0
36 | Project 36 | [9 empty] | 0 | [6 empty] | 0 | 0
37 | Project 37 | [9 empty] | 0 | [6 empty] | 0 | 0
38 | Project 38 | [9 empty] | 0 | [6 empty] | 0 | 0
39 | Project 39 | [9 empty] | 0 | [6 empty] | 0 | 0
40 | Project 40 | [9 empty] | 0 | [6 empty] | 0 | 0
41 | Project 41 | [9 empty] | 0 | [6 empty] | 0 | 0

## Benefits Priority
Benefit Priority Worksheet
Benefit - for each of the below measures, rate the relative impact that the project will have on the respective measure by rating as 0, 3, 6 or 9.
Benefits are annualized.
Measure | Description | 0 | 3 | 6 | 9
Revenue enhancement ($) | Will this positively impact the revenue of the Company? | No Impact | Small < $500,000 | Medium $500,000 - $5,000,000 | Large > $5,000,000
Reduce Cost or Cost Avoidance within Company | Will this reduce costs within the Company by decreasing or avoiding time, labor, supplies, travel? | No Impact | Small < $50,000 | Medium $50,000 - $500,000 | Large > $500,000
Increase speed of delivery (i.e., process bills faster) | Will this improve our ability to deliver results to our customers faster? | No Impact | Small | Medium | Large
Strategic Importance | Is this aligned with the Company product strategy of: Insert your strategy such as: * reducing cost * increasing speed * reducing errors * regulatory | Not linked to product or Strategy | Linked to two items | Linked to three items | Linked to all four items
Amount of Client Services "Pain" | Level of negative impact process currently has on client services | No Impact | Small | Medium | Large
Client Value | Does this deliver additional value to our clients? OR Does this deliver savings to our client? | Client not aware of any additional value | Client sees that this will add value to their offering from the Company | Client considers this critical as it brings great value to their offering from theCompany. Without this, there is a potential for client attrition. | Client considers this critical. Without this, client attrition is emminent
Business Unit Impact | The scope of the project/project impact across business units | No Impact | Impact across two departments in a single business unit | Impact on an entire Business Unit | Impact across two or more Business Units
Revenue enhancement ($)
Reduce Cost or Cost Avoidance within Company A
Increase speed of delivery (i.e., process bills faster)
Strategic Importance
Amount of Client Services "Pain"
Client Value
Business Unit Impact

## Effort Priority
Effort Priority Worksheet
Effort - For each category below, rate the relative level of effort (using a 0, 3, 6, or 9) required to meet the project's requirements. Lower scores indicate that less effort is required.
Measure | Description | 0 | 3 | 6 | 9
Personnel Requirements | The average number of FTE's (full time equivalent people) required to execute the project (independent of project duration) | 1-3 | 3-6 | 6-12 | >12
Project Duration | The number of weeks from start date to end date of the project. | < 6 weeks | 7-12 weeks | 13-25 weeks | > 26 weeks
Budget Available | Are there budgeted funds available to support this effort? | Fully coverd in current baseline budget | Business case funded by $ in the baseline budget | Budget approved but not yet funded | No current funding
Capital Investment ($MM) | Are there any incremental capital expenditures or other costs that are required to implement the project? | No Capital | Small <$1,000 | Medium $1,000-$10,000 | Large >$10,000
Risk Projection | What is the probability of not succeeding due to issues with respect to schedule, budget, customer requirements, etc? | None | Low | Medium | High
Business Unit Impact | What is the effort and coordination required across departments and Business Units? | None | Two department in a single Business Unit | Entire Business Unit | More than one Business Unit
Personnel Requirements
Project Duration
Budget Available
Capital Investment ($MM)
Risk Projection
Business Unit Impact

## Revisions
Date | Entered by | Reason